Proposal

PIPO Production Cleanup and Migration to Integration Suite

for (Customer Name)

| Client Name: (Customer Name) |  | Document No: POM/APJ25001CPA |  |
| --- | --- | --- | --- |
| Submission Date: 10-09-25 |  | Document Version: V1.0 |  |

Point of Contact:

Sharjeel Siddiqui

Contact: +966 56 585 6823

Email: sharjeel.siddiqui@craveinfotech.com

Vishal Verma

Contact: +49 160 908 19625

Email: vishal.verma@craveinfotech.com

Crave InfoTech

H.O.: 2035 Lincoln Highway Suite: 3008D Edison, NJ- 08817, USA

India office

STPI Building, Hinjewadi phase1, Pune 411057

Index

1.	Executive Summary	4

2.	About Crave InfoTech	5

3.	About #CUSTNAME	6

3.1	About the Client – #CUSTNAME Plc:	6

3.2	Business Verticals & Operational Landscape	6

3.2.1	Convenience store operations (7-Eleven)	6

3.2.2	Wholesale and retail business (CP Axtra)	6

3.2.3	Financial and supporting services	7

3.2.4	Food manufacturing and supply	7

3.2.5	Corporate structure and ownership	8

3.3	Challenges & Project Objective	8

4.	Project Scope	9

4.1	Introduction	9

4.2	Proposed Migration Approach Under Migration Factory Program	9

4.3	PIPO Assessment Results & Observation	10

4.3.1	Migration Assessment Analysis – ICOs with T-shirt Sizing	10

4.3.2	Migration Assessment Analysis – Adapter Summary	11

4.3.3	Key Considerations for Migration	11

4.4	Migration Project Realisation Scope	12

4.4.1	Solution Overview	12

4.4.2	Integration Suite Architecture	12

4.4.3	Pre-requisites & Key Assumptions	13

4.4.4	Out of Scope	13

4.4.5	Project Documents Deliverables	13

4.4.6	Bill of Material	14

4.4.7	RACI Matrix	14

5.	Project Delivery Approach	15

5.1	Project Organization Structure:	15

5.2	Project Resource Planning (Staffing)	16

5.3	Product Implementation Methodology:	17

5.4	Communication Plan	17

5.5	Issue Resolution and Escalation Procedure	18

5.6	Change Management Process	20

6.	Resource allocation, Timelines and Commercials	22

6.1	Resource Allocation	22

6.2	Project Delivery Timelines	22

6.3	Payment terms	24

7.	Sign Off	25

8.	Key Assumptions	26

8.1	Dependency on Client	26

8.1.1	IT and Infrastructure	26

8.1.2	Network and Connectivity	26

8.1.3	Customer responsibility during the implementation	26

8.2	Other Assumptions	26

8.3	Intellectual Property Rights	27

8.4	Limitation of Liability	27

8.5	General Provisions	27

# Executive Summary

<EXECUTIVE SUMMARY>

# About Crave InfoTech

We are an award-winning SAP PE build, PE-Sell & PE-Services partner who can successfully implement complete enterprise solutions, minimizing total cost of ownership, with rapid deployment and a lasting impact for efficiency and total audit-ready compliance.​

18+

INC. 5000 America’s Fastest Growing Pvt. Companies

NJBIZ Leaders in Digital Tech 2024

SAP BTP Most Valuable Partner Award

Fast 100 Asian American Business’24

SAP ACE Award 2023

Winner SAP ACE Award

SAP Pinnacle Award Finalist

SAP Hack2build Winner

APPs Validated
By ZEBRA

Awards

Certifications

Partners

50+

100+

55+

25+

Years of providing niche SAP consulting across industries

Pre-packed products specific to enterprise automation use cases

Enterprise customers served globally

SAP Business AI Use cases Built

SAP initiatives delivered globally

# About #CUSTNAME

<ABOUT CLIENT>

# Project Scope

<PROJECT_SCOPE>

R – Responsible | A – Accountable | C – Consulted | I - Informed

# Project Delivery Approach

Crave InfoTech's Project Delivery methodology has evolved with multiple project delivery experience at various organizations. Our Project Methodology is based on lean principles and adaptive to implementation needs of individual projects and client organizations internal quality processes.

## Project Organization Structure:

Below diagram shows the overall engagement team structure.  The goal is to provide a single point of accountability between Crave InfoTech and #CUSTNAME for key project activities. Based on the project need, Crave will have the best blend of onsite and offshore resource model to deliver quality solution at optimized cost.

Onsite + Offshore Teams as per project needs

A detailed RACI matrix will also be defined during the Project Initiation phase and a sample is attached below (This is sample plan. The final activity list and the responsibility will depend upon the scope and the responsibility of Crave InfoTech)

| Sr No | Activity | Responsibility |
| --- | --- | --- |
| 1 | Planning and Initiation |  |
| 1.1 | Preparation Project Plan | Crave/#CUSTNAME |
| 1.2 | Approve the Project Plan | #CUSTNAME |
| 1.3 | Necessary Amendments | Crave/#CUSTNAME |
| 1.3 | Infrastructure Readiness and System Access | #CUSTNAME |
| 2 | PIPO Assessment |  |
| 2.1 | PO Assessment Setup with Cloud Connector | Crave/#CUSTNAME |
| 2.2 | Availability of user for Assessment Tool Run | Crave/#CUSTNAME |
| 2.3 | Assessment of PIPO Production Environment | Crave/#CUSTNAME |
| 2.4 | Generate and Share Assessment Report | Crave |
| 3. | Baseline Configuration |  |
| 3.1 | Configuration of SAP Integration Suite | Crave |
| 3.2 | Configuration of Migration Connectors | Crave |
| 3.3 | Approval of the baseline configuration | #CUSTNAME |
| 4. | Project Realization |  |
| 4.1 | Migration of Simple Complexity ICOs | Crave |
| 4.2 | Migration of Medium Complexity ICOs | Crave |
| 4.3 | Migration of High Complexity ICOs | Crave |
| 4.4 | Connectors Integration testing | Crave / #CUSTNAME |
| 5. | Training |  |
| 5.1 | Facilities arrangement for training | #CUSTNAME |
| 5.2 | Making user available for training | #CUSTNAME |
| 5.3 | Conducting training for the Core team (train the trainer) | Crave |
| 5.4 | End-User training | #CUSTNAME |
| 6. | Testing – Unit, Integration and Regression |  |
| 6.1 | Prepare test scenarios | #CUSTNAME/Crave |
| 6.2 | Upload / preparation of standard test data. | #CUSTNAME |
| 6.3 | Conducting test | Crave / #CUSTNAME |
| 6.4 | Review test data | Crave / #CUSTNAME |
| 6.5 | Approval of test results | #CUSTNAME |
| 7. | Documentation |  |
| 7.1 | Prepare System Documentation | Crave |
| 7.2 | Review and approve documentation | #CUSTNAME |
| 7.3 | End User documentation | Crave / #CUSTNAME |
| 8. | Go Live Run |  |
| 8.1 | Carry out live run | Crave / #CUSTNAME |
| 8.2 | Review results of live run | #CUSTNAME |
| 8.3 | Approve and sign off | #CUSTNAME |
| 9. | Post Go-Live Support |  |
| 9.1 | Post go-live support | Crave |

## Project Resource Planning (Staffing)

During the initiation of the project Crave InfoTech Project/Program manager identifies the resource needs for the entire duration of the project. The offshore Delivery Manager then blocks the resources as per the staffing plan to ensure there is no resource crunch during the project execution, which helps to ensure the project deliveries are on track.

Below table provides the indicative staffing requirements for different project phases that includes execution/implementation activities. During project initiation/planning phase this list will be revisited for any changes.

| Project Phase | Functional Consultant | Technical Consultant | Other (Developer, Tester, PM, UI5.ABAP etc.) |
| --- | --- | --- | --- |
| Project Preparation | Yes | No | PM (Crave and #CUSTNAME) |
| PO Migration Assessment | Yes | Yes | PM, Integration Developer |
| Realization- Migration | No | Yes | PM, Integration Developer |
| Unit and integration testing | Yes | Yes | PM, Integration Developer & QA |
| Documentation and user training | Yes |  | QA/Trainer |
| Cut Over and Go Live | Yes | Yes | PM, Integration Developer & QA |
| Post Go Live Support | Yes | Yes | PM, QA, Technical Support |

## Product Implementation Methodology:

Crave InfoTech's implementation methodology has been incorporated with multiple implementation experiences. Our methodology is based on lean principles and adapts to implementation needs.

This section describes our 6 phase implementation methodology covering the activities to be performed in each phase and the deliverables to be produced in those phases.

## Communication Plan

Following table represents different reports that will be generated periodically and circulated to various stakeholders.

| Exhibit: Daily Interaction |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Communication Mode | Report Recipient/s | Frequency | Comments |
| Daily Status Report | Email/Telephone | Crave InfoTech and #CUSTNAME Project Manager | Daily | Daily Status Reports informs the project tasks executed on a daily basis |
| Weekly Status Reports | Email | Crave InfoTech and #CUSTNAME Project Manager | Weekly | Summarize the tasks delivered & issues from the previous week(s), activities planned for the next week & specific events. Project Effort and Schedule Variance |

Additional meetings will be decided during project planning phase as necessary.

## Issue Resolution and Escalation Procedure

Crave InfoTech’s Project Manager will identify and capture project related issues that adversely impact the project, launch relevant actions to resolve them, and track and monitor the issues to closure. The Crave InfoTech’s Project Manager will also decide on the appropriate escalations for any critical/unresolved issues.

The responsibilities / timescales for executing these procedures are:

| Issue Management |  |  |
| --- | --- | --- |
| Task | Timescale | Responsibility |
| Raise Issue Report | As they occur | Any person working on or related to the project |
| Assessment/ Management of issues | Weekly/periodically | Crave InfoTech Onsite Project Manager |
| Reporting | Periodically | Crave InfoTech Onsite Project Manager |

Following guidelines will be followed for reporting the issues:

- Develop issue report containing problem description and suggested solution. Report to Crave InfoTech Project Manager

- Issues will be documented in issue reports and in the project’s issue log.

- The Crave InfoTech Project Manager is responsible for problem classification together with the issue reporter

- The Crave InfoTech Project Manager will convey the issue to the issue owner and define actions. If the problem is serious or critical, an issue report will be sent with an meeting invite

- The Crave InfoTech Project Manager assign the action to the issue owner or/and action owner

- The Crave InfoTech Project Manager will monitor and follow up the action plan

- The Crave InfoTech Project Manager will terminate the problem handling process when the problem is solved or decided closed

Following exhibit explains the process of issue classification:

| Issue Classification |  |  |  |
| --- | --- | --- | --- |
| Problem Type | Definition | Reporting process | Solution Responsible |
| Low | Implies none or low project delay and/or cost increase. | Report to Crave InfoTech Project Manager. Issue handled within the project. | - Crave InfoTech Project Manager |
| Serious | Implies serious project delay and/or cost increase or influence on working relation. | Report to Crave InfoTech Project Manager and Crave InfoTech Delivery Manager. Inform #CUSTNAME Project manager responsible | - Crave InfoTech Project Manager - #CUSTNAME Project Manager |
| Critical | Implies critical treat against the project or working relation. | Immediately report to Crave InfoTech Project Manager, Crave InfoTech Delivery Manager and the member of the Project Core Committee including #CUSTNAME representative | - Crave InfoTech Project Manager - #CUSTNAME Project Manager |

Following escalation process will be followed as part of the issue management:

| Exhibit : Escalation Process |  |  |  |
| --- | --- | --- | --- |
| Issue Type | Escalation Point | Escalation Criteria | Governance Role (Project Core Group) |
| Project Delivery | Crave InfoTech Project Manager | If plan to resolve the issue is not outlined within 48 hrs (24 hrs in case of urgent issues) | Weekly checkpoints (or depending on the urgency) Issue resolution Quality issues |
| - Contract - Unresolved delivery issue - Program Management issue within specified timeframe | Crave InfoTech Delivery Manager | If plan to resolve issue is not outlined within 48 hrs (24 hrs in case of urgent issues) | Monthly Review As needed in case of urgent issues |

** The Project Workgroup will be comprised of representatives from Crave InfoTech and #CUSTNAME key project stakeholder.

## Change Management Process

Crave InfoTech defines Change as “a state different from a previously defined condition”.  The goal of Crave InfoTech’s change management process is to ensure that standardised methods and procedures are used for efficient and prompt handling of all changes, in order to minimise the impact of change-related incidents upon service quality, and consequently to improve the day-to-day operations of the in the scope of the project.

Crave InfoTech proposes the following Configuration and Change Management process:

- #CUSTNAME will submit all change requests (Addition, modification, deletion requests related to project scope, environment changes etc.) to Crave InfoTech Project Manager

- Crave InfoTech Project Manager will analyse the impact of the change from implementation perspective.

- In case where the change requested has significant impact and risks to overall success of the project, Crave InfoTech Project Manager will put the request on ‘Hold’ and discuss the impact and the risks involved with #CUSTNAME Project Manager.

- Crave InfoTech Project Manager will plan the implementation timeline to ensure minimal impact to the overall Project timelines.

- Crave InfoTech Project Manager will keep all the stakeholders informed about the changes to project timelines.

- Crave InfoTech Project Manager will keep a change log of all changes that have been made.

- Crave InfoTech Project Manager will ensure that version control is managed

Change Management process will primarily cover the following areas:

- Project Requirements (Project Scope)

- Implementation Environment

- Third party dependencies

# Resource allocation, Timelines and Commercials

## Resource Allocation

Crave Infotech will deploy following team for this project execution –

<RESOURCE_PLAN>

#CUSTNAME will deploy following team for this project execution –

| Crave Resources | Location | Allocation | Resource Count |
| --- | --- | --- | --- |
| #CUSTNAME Project Manager | On-site | Partial | 1 |
| Developers | On-site | Full Time | 2 |
| QA/Business Analyst | On-site | Partial | 1 |

#CUSTNAME will assign their respective required project team during the project. On request from #CUSTNAME we have reduced the number of integration developers enabling #CUSTNAME team to have their integration developers collaborate with Crave team. They will have to adhere to the project timeline during all phases for needful accesses, approvals, availability of resources and testing. Any delay in timeline due to non-availability of resources form #CUSTNAME, will increase the project cost for the additional number of days for Crave resources.

## Project Delivery Timelines

Considering the fact that #CUSTNAME’s production have some inactive ICOs which needs to be cleaned before migrating to Integration Suite, Crave suggests phases in project delivery, mainly–

Phase 1: Setup, configure and clean-up of inactive interfaces

Phase 2: Migrate interfaces as per the standard migration protocol under migration factory program.

These phases are combined in one project delivery plan listed below -

Following will be the commercials of this project –

| Sr. | Particulars | Total Cost in SGD |
| --- | --- | --- |
| 1 | Migration from PIPO to Integration Suite with Shared Resources (Including PO Clean-up) | USD. XXXX /- |
| Total Project Cost |  | USD. XXXX /- |
| In words: XXXX Dollars Only |  |  |

Terms / Notes:

- This price is inclusive of inactive or redundant ICO cleaning from #CUSTNAME’s PIPO system. The cleaning phase is for around a month and both #CUSTNAME and Crave teams would work together.

- The quoted price is considering collaborative effort estimation. #CUSTNAME team is liable to provide 2 integration developers/consultant throughout the project. The Integration developers/consultant must meet Crave’s quality standards for the project to be executed in the promised timeline.

- Prices are exclusive of VAT or any local taxes.

- Crave’s team will handle the project remotely, if the client wants any resource to travel on-site, the cost to fulfil such request will be calculated at actual on FTA basis and shall be charged separately.

- Any delay due to #CUSTNAME Approval process / UAT process or Delay in dependent activity will impact the implementation timeline.

## Payment terms

| Sr. No. | Payment milestones | % of total payment |
| --- | --- | --- |
| 1 | Advance with PO | 30% |
| 2 | After Simple Complexity Interfaces Migrated to Integration Suite | 20% |
| 3 | After Medium Complexity Interfaces Migrated to Integration Suite | 20% |
| 4 | After Large Complexity Interfaces Migrated to Integration Suite | 20% |
| 5 | After UAT, Verification & Testing & Go Live is Complete | 10% |

- Pyment to be released in Net 30 days from the date of invoice

# Sign Off

IN WITNESS WHEREOF, Crave InfoTech and #CUSTNAME have each caused this Project SoW to be executed by their respective duly authorized officers as of the Effective Date.

The undersigned agree to the terms of this proposal on behalf of his or her organization or business.

#CUSTNAME			         				Crave InfoTech

By:					           			By:

Authorized Signature 						Authorized Signature

Name	 								Name - Vrushali Nistane

Date: 									Date: 10th September, 2025